## query
ID | Title | Modification Type | Modification Category | Modification Reason | Requester's Name | Request Date | Region | Applicable Location(s) | Applicable Product Type(s) | Business Description of the Modification | Assigned To | Risk Data Element(s) Details | Implementation Date | Status | Sign-off Status | GFCC-RMO Notes | Required Approver(s) | Approval Status | PIV Created | Updated | Modified | Created By | Open with Seclore | Item Type | Path
121 | DE AT - PEP HRO Update - HR PEP's only | Change | High Risk Override | Regulatory Requirement | Sasha Hopkins | 2024-07-24 | EMEA | Germany and Austria. | All products for AEESA-DE, AEESA-AT, AEPE-DE and AEPE-AT. | Customer Risk Element: Only customers with a HIGH-RISK PEP Risk Score to receive a High-Risk Override (HRO). Currently all customers who are a PEP receive a HRO in the CRR regardless of the PEP Risk Score. Going forward the CRR should consider the PEP Risk Score of the PEP and only apply a HRO for PEPs with a HIGH-RISK PEP Risk Score. Please can you provide a volume impact assessment for the above outlined change prior to proceeding for approvals to implement? Attached original request form from the MCO. | Anna De Nicolais |  PEP Foreign element was reactivated by changing the weighting from 0 to 200 points.  PEP Present element was modified by changing the weighting from 4000 to 100 points.  PEP Risk Rating element reactivated by changing the weighting from 0 to 200 points, and the following rules applied, as per CRR Customization Form n.121: - 2: Low and Medium Risk PEP on the account (400 points) - 20: High Risk PEP on the account (HRO) | 2025-01-16 | Completed |  | To be completed with CRR Customization Form 141 as part of the Certification effort. Completed on 1/16/25 CMC-2025-001 | Alex Redpath;#32;#Barbara Musiol;#182 |  | 2025-01-27 13:22 | Yes | 2025-01-27 13:22 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
141 | Certification DE/AT | Change | Data Element Weighting Value | Regulatory Requirement | Barbara Musiol | 2024-12-06 | EMEA | Germany and Austria | All | Certification changes to meet local requirements. More details in the attached documents. | Anna De Nicolais | HROEMD: - integrated. BRGLST: - integrated. PEP Foreign: - Reactivated w.200 PEP Present - Reactivated w. 100 PEP Risk Rating: - 2: Low or Medium Risk PEP on the account (added low) - 20: High Risk PEP on the account (added HRO) SIP-SIE Present on Account: - Add Char: SIE added to the file as part of SIP/SIE remediation. Cash Payment - zeroed out Cash Payment Domestic Amount/Count: - Zeroed out Cash Payment Foreign Amount/Count: - Zeroed out Foreign bank ACH/DD Amount: - Foreign ACH/Direct Debit Transaction Amount outside of EU < $2000 in last 12 months - Foreign ACH/Direct Debit transaction Amount outside of EU >= $2000 and < $5000 in last 12 months - Foreign ACH/Direct Debit Transaction Amount outside of EU >= $5000 in last 12 months Foreign bank ACH/DD count: - Foreign ACH/Direct Debit Transaction Count outside of EU =4 in last 12 months - Foreign ACH/Direct Debit Transaction Count outside of EU >4 in last 12 months Transactions in EU High Risk Jurisdictions or FATF: remove FATF from all rules - Wire payment in the last 12 months >€5,000 EUR ($6,000 USD) in last 12 months Wire Payments Domestic - Amount - Domestic Wire Payment Transaction Amount within the EU < $2000 in last 12 months - Domestic Wire Payment Transaction Amount within the EU >= $2000 and < $5000 in last 12 months - Domestic Wire Payment Transaction Amount within the EU >= $5000 in last 12 months Wire Payments Domestic - Count (Wrong file in rule, need EU file) - Domestic Wire Payment Transaction Count within the EU < 4 in the last 12 months - Domestic Wire Payment Transaction Count within the EU >= 4 and <= 7 in the last 12 months - Domestic Wire Payment Transaction Count within the EU >= 8 and <= 12 in the last 12 months - Domestic Wire Payment Transaction Count within the EU > 12 in last 12 months Wire Payments Foreign - Amount - Foreign Wire Payment Transaction Amount outside of EU < $2000 in last 12 months - Foreign Wire Payment Transaction Amount outside of EU >=$2000 and <$5000 in last 12 months - Foreign Wire Payment Transaction Amount outside of EU >=$5000 and <$10,000 in last 12 months - Foreign Wire Payment Transaction Amount outside of EU >= $10000 in 12 months Wire Payments Foreign - Count - Foreign Wire Payment Transaction count outside of EU <4 in last 12 months - Foreign Wire Payment Transaction count outside of EU >=4 and <=7 in last 12 months - Foreign Wire Payment Transaction count outside of EU >=8 and <=12 in last 12 months - Foreign Wire Payment Transaction count outside of EU >12 in last 12 months | 2025-01-16 | Completed |  | The GFCC-CRR has reviewed the AT & DE configuration with the MCO and Regional Oversight teams to make sure that customized lists, ARF/HRO decommissioning, and enterprise enhancements have been analyzed and changes identified to meet regulatory requirements. Details are in the attached documents. Includes CRR Customization Form n. 121 | Barbara Musiol;#182;#Martin Schaub;#209 |  | 2025-01-20 08:04 | Yes | 2025-04-23 05:47 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
139 | GNS Partners - CRR Updates | Add | Data Element Weighting Value | Best Practice | Tommy Colbert | 2024-11-25 | Global | -A, -E, -J | GNS-PARTN | Enhancements to the CRR scoring to more accurately identify risks associated with the GNS partners. This includes PEP risk, geography Very High corruption risk and authoritative source geography risks. Details in the attachment | Jacob W Young | Removed product as a secondary data point rule that was excluding GNS from the following rules: PEP Present element: 100 points PEP Foreign element: 200 points PEP Risk Rating element: Medium Risk PEP on the account (400 points) High Risk PEP on the account (600 points) Created the following elements/rules: GNS - Cntry EU High Rsk Thrd: 600 points GNS - Country on Non-coop Tax: 300 points GNS - Country on FATF List: 600 points: 600 points GNS - Corruption Rsk of Geo: 4000 points | 2025-01-22 | Completed |  | CMC-2025-005 | Al M Brown;#402 | Approved | 2025-01-23 09:29 | Yes | 2025-01-24 09:52 | Tommy Colbert |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
124 | IT - FATF Revised Approach Testing | Change | High Risk Override | Best Practice | Sasha Hopkins | 2024-08-14 | EMEA | Italy | All products under LE's for Italy | Recently it was agreed with the wider EMEA markets that the approach to the FATF Grey List and Jurisdictions under Increased Monitoring would be amended given the recent additions of jurisdictions such as Croatia and Bulgaria, and the subsequent volume impacts which occurred as a result. At the time Italy had elected to be excluded from the testing due to market requirement, however they would now like to test this EMEA approach for their list also. To confirm the parameters for testing are as follows: Remove current HRO - as it stands today, any customer address which falls under a FATF listed jurisdiction will be attributed and automatic HRO Attribute all jurisdictions which fall under the FATF list a high-risk score of ‘9’ – this would act to apply a multiplier of 9 o Please note - this change would mean that the FATF jurisdictions will remain included in the HRJ TM rules, however this is something which will be assessed for applicability as we move forward in reviewing the effectiveness of the TM HRJ rules. Remove the Foreign Jurisdictions element o Rely on the geography elements only (utilizing the Refinitiv scoring). Please can you review complete a volume impact assessment for us to share with the market? Let me know if further information is required. |  |  | 2025-01-30 | Completed |  | To be completed during the Certification process. For more details see CRR Customization Form 146. | Valentina Finazzo;#409 | Approved | 2025-01-30 12:59 | Yes | 2025-01-30 12:59 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
146 | Certification IT | Change | Data Element Weighting Value | Best Practice | Debora Pelloni | 2025-01-27 | EMEA | IT | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified and changes were made to meet local requirements and align with EMEA standards (PEP and FATF). More details in the attached documents. This request includes CRR Customization Form n.124. | Anna De Nicolais | Occupation Industry Type and Job Code elements multiplier was increased from 3 to 7 to align with the approach used in EMEA. Country on FATF List elements was modified from an HRO applied to all countries on the FATF list to an HRO applicable only to countries on the FATF High-Risk Jurisdictions subject to a Call for Action list. Foreign Jurisdiction element was decommissioned to align with the approach used in EMEA. HROEMD and BRGLST were integrated. FESTRA, FESTRN, GXTRA, GXTRN, TRNHRO, TRNARF and USCS02 to be decommissioned. | 2025-01-30 | Completed |  | Includes CRR Customization Form 124. CMC-2025-008. | Valentina Finazzo;#409 | Approved | 2025-01-30 12:58 | Yes | 2025-03-24 12:38 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
149 | Certification - FI, DK, NO, SE | Change | Data Element Weighting Value | Best Practice | Carl Ericsson | 2025-02-13 | EMEA | FI, DK, NO, SE | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified and changes were made to meet local requirements and align with EMEA standards. More details in the attached documents. | Anna De Nicolais | HROEMD: - integrated. BRGLST: - integrated. Structure: - HRO for NPO and Charities (Associations excluded due to data remediation in the market) PEP Risk Rating: - Low and medium risk PEP mult of 2 instead of 4.5 SIP-SIE present on account: - SIE added to the file (no indicator as there could be duplicated point since no HRO elected) Foreign Jurisdiction: - Address in a Foreign Jur: mult from 1 to 2 ATM Withdrawals Foreign Count: - from HRO to ARF3: Withdrawal in EU High Risk Third country in the last 18 months Cash transactions: - zeroed out Spend greater than Income: - added Consumer - Spend over 150% of annual income - modified Consumer - Spend between 100% and 150% of annual income - removed Consumer - Spend between 50% and 75% of annual income TM alert in past 18 months - ARF1 for accounts with 3 or more TM-alerts within the past 18 months to capture diverse OOP activity TM Rule : Third Party Wire Payment: - zeroed out as covered by the TM alert in past 18 months rule HRO/ARFs decommissioned: - BRGLST, FESTRA, FESTRN, HROEMD, GXTRA, GXTRN, TRNARF, TRNHRO | 2025-02-17 | Completed |  | CMC-2025-021 |  | Approved |  | No | 2025-04-21 13:25 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
152 | IN Occupation Element Enhancements | Add | Data Element Weighting Value | Examiner Expectation | Jacob W Young | 2025-02-25 | APAC | India | All individual type products | Incorporate the newly created Occupation Status data point into the assessment of Occupation. These changes are being made to address an RBI finding concerning the use of the same level of occupation risk for all customers irrespective of their actual occupation risk. With the mapping of occupation codes to risk ratings, and the added ability to assess occupation status, the CRR is able to more accurately assess occupation based on available data. | Jacob W Young | Occupation status codes were assigned a risk rating based on their description. Occupation job codes for which a description was obtained were assigned a risk rating. Created IN-Occupation element to incorporate the newly created Occupation Status data point into the assessment of Occupation. The new data point is being used in conjunction with the existing Occupation Code data point. The element and rule configuration is as follows: o Weighting = 30 o Default Multiplier = 7 o Rules: Fundamental Assessment risk rating for Occupation Type Code Fundamental Assessment risk rating for Occupation Job Code Changed Weighting of Occupation (Job Code) element from 30 to 0 as it is being replaced by the IN-Occupation. | 2025-02-27 | Completed |  |  | Vineet D Dhamija;#87 | Approved |  | No | 2026-02-06 13:14 | Jacob W Young |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
154 | GNS Partners - Country on Authoritative Source List | Change | Data Element Weighting Value | Best Practice | Jacob W Young | 2025-02-27 | Global | -A -J -E | GNS-PARTN | The line of business is requesting to combine the assessment of EU High Risk Third, FATF, and Non-Cooperative Tax jurisdiction lists into a single element rather than in separate elements as they are currently. This is due to there being countries that could be on more than one list, therefore triggering more than one element for the same attribute (party's address country) | Jacob W Young | Change weight of the following elements to 0: GNS - Cntry EU High Rsk Thrd GNS - Country on FATF list GNS - Country on Non-coop Tax Create new element: GNS - Cntry on Auth Srce List Create three rules under the new element to replicate the logic in the three elements listed above | 2025-03-04 | Completed |  | CMC-2025-033 | Al M Brown;#402 | Approved |  | No | 2025-03-05 16:49 | Jacob W Young |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
132 | ES - MARB-H integration/modification | Change | High Risk Override | Best Practice | Marcos Sanchez Toledo | 2024-09-17 | EMEA | Spain | SE-DIR | Remove: 29640 - Fuengirola 29680 - Estepona 29650 - Mijas 29649 - Mijas 29631 - Benalmadena 29630 - Benalmádena 29620 - Torremolinos Add: 29679 Benahavís (Marbella) | Jacob W Young | The logic for MARB-H is coded in the backend. CADENCE tech development was required to update the list of postal codes. | 2025-03-05 | Completed |  | The feature has been added to the backlog for prioritization This feature is part of PI 24.1. A manual impact assessment was completed. Because the impact assessment contains PII, a summary of the impact has been attached. Please reach out to RMO team for additional details. | Natalia E Gonzalez;#196 | Approved |  | No | 2025-03-05 09:27 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
147 | Update Multiplier for HR PEP | Change | Data Element Weighting Value | Examiner Expectation | Melisa Martinez | 2025-01-30 | LACC | México. | All existing products in the México market. | High Risk Pep should be flagged automatically as High-Risk Costumers, so the multiplier has to be modified in a way that instead of x3, it will be multiplied x20, so all high risk PEP on the account should receive 4,000 points. MX was elected as pilot market for KYCR and EDD standards that expect to combine both EDD and PEP reviews. The pilot is planned to start in April and we will need this change to be in production before then. | Anna De Nicolais | PEP Risk Rating: - Multiplier changed from 3 to 20 for High Risk PEPs | 2025-03-05 | Completed |  | HRO applied to High Risk PEPs | Jenifer N LopezCardona;#36 | Approved |  | No | 2025-03-05 13:32 | Melisa Martinez |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
155 | HROEMD decommission for D0, D2, D3, D4 centers | Remove | High Risk Override | Best Practice | Jacob W Young | 2025-02-28 | US | D0 D2 D3 D4 | All | Expire HROEMD HRO for D0, D2, D3, and D4 centers as this was missed during the implementation of the HROEMD elements and rules. | Jacob W Young | Expire HROEMD HRO on HRO/ARF Definition page for D0, D2, D3, and D4 centers | 2025-03-06 | Completed |  | CMC-2025-034 | Robert J Garcia;#117 | Approved |  | No | 2025-03-06 10:04 | Jacob W Young |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
158 | UK/X1 Structure File Correction | Remove | Data Element Weighting Value | Best Practice | Anna De Nicolais | 2025-03-13 | EMEA | UK/X1 | All | The csv file used in the rule logic of element ‘Structure’ in UK & X1 contained default values UNKNWN, XX & OTHER that were missing in the multiplier file. This mismatch resulted in dual scoring for certain accounts where multiple structure codes were present. To resolve this, we updated the csv file by removing the default codes (UNKNWN, XX & OTHER) to align with the multiplier file. This ensures that accounts are assigned a single risk rating for the element based on the intended structure code. | Richa Khullar | Company Structure - Updated the csv file by removing the default codes (UNKNWN, XX & OTHER) | 2025-03-21 | Completed |  | CMC-2025-040 |  |  |  | No | 2025-03-25 23:50 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
156 | Certification - Repats | Change | Data Element Weighting Value | Regulatory Requirement | Jaime F Murias | 2025-03-05 | EMEA | Bulgaria, Croatia, Cyprus, Estonia, Greece, Iceland, Ireland, Latvia, Lithuania, Malta, Portugal, Romania, Slovakia, Slovenia and Switzerland | All | Certification changes to align with ES | Richa Khullar | BRGLST: - integrated. Structure: - New HRO codes added Industry: - New ARF1, ARF3 & HRO codes added to the existing list - HROs removed from CHARITY, TRUST & CASINOS industry type codes Geography of BO: - Element weighting reduced from 100 to 50 SIP-SIE present on account: - SIE added to the file as part of SIP/SIE remediation - New rule added to capture SIP indicator Cash transactions: - zeroed out Geography Overrides: - Override of 9 removed for AL,GD,LC,LI,LR,MO,MS,MU,NR,VC HRO/ARFs decommissioned: - BRGLST, BGMERH,ESLOCH, FESTRA, FESTRN, GXTRA, GXTRN, LVMERH, PEPHGH, PTMERH, SLMERH, TRNARF, TRNHRO. | 2025-05-05 | Completed |  | The GFCC-CRR has reviewed the Repats configuration with the MCO and Regional Oversight teams to make sure that customized lists, ARF/HRO decommissioning, and enterprise enhancements have been analyzed and changes identified to meet regulatory requirements. Details are in the attached documents. CMC-2025-056 | Natalia E Gonzalez;#196 | Approved |  | No | 2025-05-21 06:03 | Richa Khullar |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
115 | UK HRI Addition Volume Impact - 142 - Political Organisations | Add | High Risk Override | Best Practice | Sasha Hopkins | 2024-06-25 | EMEA | UK & X1 | All LoB's | The UK MCO have requested to add industry code142 - Political Organisations to their HRI list and add an HRO, and as such we would like a volume impact assessment to understand how many customers fall under this industry code. They have a case at the moment with the Conservative Party, where the business would like to proceed with the relationship, but our Compliance advice is that EDD should be applied (along with some other bespoke controls). Currently its classified as 8 in the fundamental assessment, but this would only account for an additional 320 points in the CRR which we wont think is commensurate with the financial crime risk and the would like this prioritised given the upcoming elections and political movements in the UK. | Anna De Nicolais |  | 2025-05-27 | Completed |  | One account currently triggers Industry Code W142. Request will be worked as part of CRR Customization Form n.128. This request will be integrated with Certification - CRR Customization Form 136. 12/02/24: to be addressed with industry codes EMEA harmonization. Will be completed with CRR Certification Form 157 |  |  |  | No | 2025-05-28 07:20 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
128 | UK - HRI Sandbox Request | Change | High Risk Override | Regulatory Requirement | Sasha Hopkins | 2024-08-29 | EMEA | UK & X1 | all in UK & X1 | We are currently reviewing the UK & X1 HRI lists to ensure the lists accurately reflect the relevant industries. For this review we have revised both the GCS & GMS lists (attached) and have assigned either HRO or ARF accordingly. Please can you run a sandbox/volume impact assessment for these updates as outlined? Noting that we would like this run with the settings used for the most recent July UK sandbox and the wider market updates. Let me know if you have additional questions - many thanks! | Anna De Nicolais |  | 2025-05-27 | Completed |  | This request will be integrated with Certification - CRR Customization Form 136. 11/26/24 On hold, due to EMEA harmonization. Will be completed with CRR Certification Form 157 |  |  |  | No | 2025-11-12 05:32 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
151 | UK Third/UK Local List Update - Feb 2025 | Change | High Risk Override | Regulatory Requirement | Sasha Hopkins | 2025-02-25 | EMEA | UK & X1 | all LoB's under UK & X1 | The following changes have been made to the UK Third Countries/Local lists as of 21st February 2025, in line with the most recent FATF publication: Added: Lao PDR, Nepal Removed: Philippines Please update the lists accordingly and increase these countries to a risk score of 9. https://www.fatf-gafi.org/en/publications/High-risk-and-other-monitored-jurisdictions/increased-monitoring-february-2025.html | Anna De Nicolais |  | 2025-05-27 | Completed |  | Completed as part of CRR Customization Form 168 - FA Geo Refresh and FATF Feb 25 changes. | Jacob W Young;#21;#Alex Redpath;#32;#Mano N Psihopedas;#418 |  |  | No | 2025-05-28 07:17 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
157 | UK HRI - Update | Add | High Risk Override | Regulatory Requirement | Sasha Hopkins | 2025-03-11 | EMEA | UK - X1 | CORP & GMS UK & X1 | Please can you add the following industry codes as HRO for UK & X1 as requested by the MCO: Proliferation- USIC84220 Defence activities USIC25400 Manufacture of weapons and ammunition Pawn Shops- W280 Pawn Brokers Political Orgs- W142 POLITICAL ORGANIZATIONS* | Anna De Nicolais | Industry: HRO added to Industry Codes: - USIC84220 - USIC25400 - W280 - W142 | 2025-05-27 | Completed |  | Covers CRR Customization Forms 115, 128. CMC-2025-025 | Louise Emma Johnston;#132 | Approved |  | No | 2025-05-28 07:27 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
162 | EMEA HRJ Risk Score adjustments for Albania & Cayman slands | Change | Country Risk Rating Thresholds | Regulatory Requirement | Sasha Hopkins | 2025-03-21 | EMEA | EMEA | All in EMEA | It was identified via the certification process that Albania and the Cayman Islands have overrides to risk score "9" which are no longer required for most of the EMEA markets. Please can you revert the risk score for Albania back to it's natural risk score for all EMEA markets. Please can you revert the Cayman Islands for all EMEA markets EXCEPT Spain/E1, CEE and the repats where this remains on the local HRO list. The BE and NL lists are still under review and may remain, this is to be confirmed. | Richa Khullar |  | 2025-05-27 | Completed |  | Should it also be maintained in E1? Overrides removed as requested. Overrides were in place as during the alignment on FATF element decommissioning it was decided to hold off making updates to the FATF list (Oct 23 changes) Since KY was confirmed as a HRJ by the market MCO for NL & BE centers, KY was retained. | Alex Redpath;#32 |  |  | No | 2025-06-02 03:43 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
168 | FA Geo Refresh and FATF changes (Feb 21, 2025) | Change | Country Risk Rating Thresholds | Best Practice | Anna De Nicolais | 2025-05-21 | Global | All | All | Each year, the CRR team conducts a refresh of the Geography Fundamental risk ratings, based on the LSEG World-Check tool, authoritative sources (FATF) and/or internally Amex designated high-risk/prohibited countries. | Anna De Nicolais | Each year, the CRR team conducts a refresh of the Geography Fundamental risk ratings, based on the LSEG World-Check tool, authoritative sources (FATF) and/or internally Amex designated high-risk/prohibited countries. The following changes in risk level occurred: • French Polynesia increased to high risk • Guatemala increased to high risk • Palestine increased to high risk • Togo increased to high risk • Western Sahara increased to high risk • Cook Islands increased to medium risk • Israel increased to medium risk • Niue increased to medium risk • Marshall Islands decreased to low risk • Saint Kitts & Nevis decreased to low risk On February 21, 2025, the following changes were applied to the FATF Jurisdictions Under Increased Monitoring and the UK High Risk Third Countries lists: • Added: Laos PDR and Nepal • Removed: Philippines As a result of the above changes: • Laos PDR and Nepal have been added to the FATF Jurisdictions Under Increased Monitoring and UK High Risk Third Countries lists; • Philippines has been removed from the FATF Jurisdictions Under Increased Monitoring and UK High Risk Third Countries lists; • French Polynesia, Guatemala, Palestine, Togo, Western Sahara were added to the High Risk Country list in markets where not already included. • Additional details on countries changing risk score but not risk level can be found in the attached document. | 2025-05-27 | Completed |  | See attached file for details and impact of the changes. CMC-2025-084 | Alex Redpath;#32;#Wendy M Ward;#82;#Robert J Garcia;#117 | Approved |  | No | 2025-05-28 10:17 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
164 | Certification - TW | Change | Data Element Weighting Value | Best Practice | Ivy Shen | 2025-04-16 | APAC | Taiwan | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified and changes were made to meet local requirements and align with APAC standards (PEP and FATF). | Anna De Nicolais | Prohibited Country (Cuba, Iran, North Korea, Syria) - from 100 to 4000 points Spend Greater than Income - Consumer - Spend between 50 and 75 percent of annual income - Consumer - Spend between 75 and 100 percent of annual income - Consumer - Spend greater than 100 percent of income BRGLST - Integrated Higher Risk Postal Codes in Country - Removed as not applicable to market SIP-SIE Present on Account - SIE added to the file as part of remediation HRO/ARFs decommissioned: - BRGLST, FESTRA, FESTRN, GXTRA, GXTRN, TRNARF, TRNHRO, USCS02 | 2025-07-01 | Completed |  | The GFCC-CRR has reviewed the TW configuration with the MCO and Regional Oversight teams to make sure that customized lists, ARF/HRO decommissioning, and enterprise enhancements have been analyzed and changes identified to meet regulatory requirements. Details are in the attached documents. | Ben F Kuo;#479 | Approved |  | No | 2026-02-06 13:14 | Richa Khullar |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
134 | Thailand CRR Customization | Add | Data Element Weighting Value | Regulatory Requirement | Estee Ho | 2024-10-16 | APAC | Thailand | All products in Thailand - consumer and corporate | For individual Cardmembers, BO and Authorized Signers, if nationality details are missing, there should be a default to a high risk for nationality. This does not override the account to an overall high risk. | Anna De Nicolais |  | 2025-08-06 | Completed |  | A default multiplier of 3 was applied to the Nationality of AH and BO elements to add 150 points (equivalent to points received by nationalities in high risk countries) to accounts where the nationality of AH and Bo is missing. Completed with CRR Certification process, CRR Customization form 165, CMC-2025-112. | Estee Ho;#91 | Approved |  | No | 2025-08-06 10:23 | Estee Ho |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
144 | Certification - NL | Change | Data Element Weighting Value | Best Practice | Johan Lenderink | 2025-01-06 | EMEA | NL | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified and changes were made to meet local requirements and align with EMEA standards. More details in the attached documents. | Anna De Nicolais | HROEMD: - element zeroed out due to FIU procedures and left as systematic HRO BRGLST: - Integrated Geography dependent elements updated with new high risk file: Nat AH (High) Nat BO (High) Geography of AH: - Def Mult from 9 to 7 Local HRJ element added: - NL Local HRJ list created Cross Border SpdCnt dif HRJ (w.200) - Cross Border Spend count of different High Risk Jurisdictions is equal to 2 or 3 in last 12 months (mult 1) - Cross Border Spend count of different High Risk Jurisdictions is equal or greater than 4 and less than 7 in last 12 months (mult 2) - Cross Border Spend count of different High Risk Jurisdictions is equal or greater than 7 in last 12 months (mult 3) Cross Border Spend HRJ Amount (w.100) - Cross Border Spend amount in High Risk Jurisdictions is equal or greater than $5,000 and less than $10,000 in last 12 months (mult 1) - Cross Border Spend amount in High Risk Jurisdictions is equal or greater than $10,000 and less than $25,000 in last 12 months (mult 2) - Cross Border Spend amount in High Risk Jurisdictions is equal or greater than $25,000 and less than $40,000 in last 12 months (mult 3) - Cross Border Spend amount in High Risk Jurisdictions is equal or greater than $40,000 in last 12 months (mult 4) Cross Border Spend HRJ Count (w.300) - This rule adds points when the number of spend transactions in high risk jurisdictions is greater than 5 Wire Pymnt Source (High) Country on Local HRJ List - element added Decommissioned: BRGLST, FESTRA, FESTRN, GXTRA, GXTRN, TRNHRO, and TRNARF Overrides removed from Albania (AL), Western Sahara (EH), Guatemala (GT), Bangladesh (BD), Djibouti (DJ), Equatorial Guinea (GQ), Honduras (HN), India (IN), Comoros (KM), Madagascar (MG), Russian Federation (RU), Chad (TD). Overrides maintained in Antigua and Barbuda and Costa Rica due to AML/CTF risk | 2025-08-06 | Completed |  | CMC-2025-017 | Johan Lenderink;#137 | Approved |  | No | 2025-08-06 10:02 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
165 | Certification - TH | Change | Data Element Weighting Value | Best Practice | Suphakrit Setthamangkorn | 2025-04-24 | APAC | Thailand | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified and changes were made to meet local requirements and align with APAC standards. More details in the attached documents. | Richa Khullar | BRGLST - Integrated Nationality of AH Ind: market asked on 5/19 to replace the rules in place in SG and limit the def mult to Individual. - Def Mult of 3 - 1: This rule adds points when the customers nationality is in a medium risk jurisdiction. - 3: This rule will add points when the nationality of the customer is in a high risk jurisdiction. - 0: This rule will add 0 points if account holder's nationality is domestic. - 80: HRO: nationality in FATF monitored jurisdictions and Myanmar. Nationality of AH Ent/Int: - 1: This rule adds points when the customers nationality is in a medium risk jurisdiction. - 3: This rule will add points when the nationality of the customer is in a high risk jurisdiction. - 0: This rule will add 0 points if account holder's nationality is domestic. - 80: HRO: nationality in FATF monitored jurisdictions and Myanmar. Nationality of BO added: - Default mutiplier of 3 - This rule will add 0 points when the account holder's nationality is in a low risk country. - This rule will add 0 points if account holder's nationality is domestic. SIP-SIE Present on Account: - This rule adds point if there is a SIP present on the account - This rule adds point if there is a SIP or SIE on the account (add char) HRO/ARFs decommissioned: - BRGLST, FESTRA, FESTRN, GXTRA, GXTRN, TH-MY, TRNARF, TRNHRO, USCS02. | 2025-08-06 | Completed |  | Includes CRR Customization Form 134. CMC-2025-112. | Estee Ho;#91 | Approved |  | No | 2026-02-06 13:14 | Richa Khullar |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
171 | PEP Risk Rating - US | Change | Data Element Weighting Value | Best Practice | Kelly T Etherington | 2025-06-19 | US | US, D0, D2, D3, D4 | All AENB, TRS | PEP Risk Rating changes to align with PEPHGH decommissioning | Anna De Nicolais | PEP - Risk Rating - D2, D3, D4 zeroed out PEP - Risk Rating - US: - HR PEP HRO: AENB and TRS products added - D0, D2, D3, D4 added | 2025-08-06 | Completed |  | CMC-2025-109 | Robert J Garcia;#117 | Approved |  | No | 2025-08-06 11:02 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
176 | Certification - HK | Change | Data Element Weighting Value | Best Practice | Suphakrit Setthamangkorn | 2025-07-22 | APAC | Hong Kong | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. More details in the attached documents. | Richa Khullar | Prohibited Country (Cuba, Iran, North Korea, Syria) - from 100 to 4000 points Spend Greater than Income - Consumer - Spend between 50 and 75 percent of annual income - Consumer - Spend between 75 and 100 percent of annual income - Consumer - Spend greater than 100 percent of income BRGLST - Integrated Higher Risk Postal Codes in Country - Removed as not applicable to market SIP SIE Present on Account - Add Char: SIE added to the file as part of SIP/SIE remediation HRO/ARFs decommissioned: - BRGLST, FESTRA, FESTRN, GXTRA, GXTRN, PEPRSK, TRNARF, TRNHRO, USCS02 | 2025-08-06 | Completed |  | The GFCC-CRR has reviewed the HK configuration with the MCO and Regional Oversight teams to make sure that customized lists, ARF/HRO decommissioning, and enterprise enhancements have been analyzed and changes identified to meet regulatory requirements. Details are in the attached documents. CMC-2025-106. | Felix K Lau;#84 | Approved |  | No | 2026-02-06 13:15 | Richa Khullar |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
107 | HRJ - Geography Fundamental Assessment - BE & NL 9 for TM | Change | High Risk Override | Regulatory Requirement | Sasha Hopkins | 2024-03-26 | EMEA | BE & NL only | All for BE & NL only | Belgium and the Netherlands have elected to include the Enterprise list in their TM rules, and as such the additional high-risk jurisdictions in the recent Geo FA (Algeria and Sint Maarten) need to be scored at a 9. Once all the Geo FA is completed and published, please can you increase the rating to 9 as outlined, Many thanks! | Anna De Nicolais |  | 2025-08-28 | Completed |  | To be completed with Certification CRR Customization Form 144 and 148 as the overrides list has been modified. | Alex Redpath;#32;#Tommy Colbert;#20 |  |  | No | 2025-08-29 11:16 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
148 | Certification - BE | Change | Data Element Weighting Value | Best Practice | Josiane Nga | 2025-02-04 | EMEA | BE | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified, and changes were made to meet local requirements and align with EMEA standards (PEP and FATF). More details in the attached documents. | Anna De Nicolais | BRGLST: Integrated Belgium Non-Profit HRO: Decommissioned as the rule logic is integrated under ‘Company Structure.’ SIP/SIE Present on Account: Rule modified to capture all SIPs - This rule adds point if there is a SIP or SIE on the account (Add Char) - This rule adds point if there is a SIP on the account (SIP Indicator) Below mentioned changes made to align with NL configuration: Structure: HRO added for Associations, Non-Profit & Trust Large No of Supps: HRO removed, multiplier changed to 4. Nationality of AH/BO: Reactivated elements PEP Foreign & PEP Risk Rating: Zeroed out. PEP Present: Wt. changed from 100 to 4000 SIP-SIE Present on Account: Wt. changed to 4000 Geography of AH: Default multiplier changed to 9. Higher Risk Postal Codes in Country: Zeroed out. TM Rule -Third party wire pay: Code 13904 added to alert type file as 1401 decommissioned. Geo overrides removed from: BD Bangladesh, People Republic of BH Bahrain, Kingdom of BM Bermuda Islands, the BY Belarus, Republic of DJ Djibouti, Republic of EH Western Sahara (formerly Spanish Sahara) FM Micronesia, Federated States of GT Guatemala, Republic of HN Honduras, Republic of IN India, Republic of JE Jersey, Bailiwick of (Channel Islands, Crown Dep of the UK) KM Comoros, Union of the LA Lao, People Democratic Republic MG Madagascar, Republic of TD Chad, Republic of (tchad) | 2025-08-28 | Completed |  | The GFCC-CRR has reviewed the BE configuration with the MCO and Regional Oversight teams to make sure that customized lists, ARF/HRO decommissioning, and enterprise enhancements have been analyzed and changes identified to meet regulatory requirements. Details are in the attached documents. CMC-2025-115. | Josiane Nga;#423 | Approved |  | No | 2025-08-29 11:10 | Richa Khullar |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
161 | UK HRJ - Barbados Risk Score Override Removal | Remove | Country Risk Rating Thresholds | Regulatory Requirement | Sasha Hopkins | 2025-03-21 | EMEA | UK & X1 | All in UK & X1 | Barbados currently still has an override of 9 for the UK & X1, where this is no longer an HRJ in these markets with a natural risk score of 3. The legacy 9 override (after the UK moved away from the EU third list in favour of the UK third/FATF monitored jurisdictions) should be removed and reverted to the natural risk score. The market have received TM alerts for customers transacting in Barbados as a result of this and is creating unnecessary volumes. I expect that this will be remediated via the geography fundamental assessment updates, however please let me know if anything else is required for this change. Thank you! | Anna De Nicolais |  | 2025-08-28 | Completed |  | Completed with CRR Customization Form 180. CMC-2025-134. |  | Approved |  | No | 2025-08-29 13:34 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
166 | UK/X1 Uganda override removal | Remove | Country Risk Rating Thresholds | Best Practice | Sasha Hopkins | 2025-05-05 | EMEA | UK, X1 | All | 9 override removal from Uganda (UG) as markets no longer apply overrides for countries on the EU Third Country list. | Anna De Nicolais | Inventory override removal for UG, | 2025-08-28 | Completed |  | Covers request made for Uganda in CRR Customization Form 103. Completed with CRR Customization From 180. CMC-2025-134 |  | Approved |  | No | 2025-08-29 13:33 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
170 | GEO FA - BE & NL increase to 9 for new jurisdictions | Change | Country Risk Rating Thresholds | Regulatory Requirement | Sasha Hopkins | 2025-05-28 | EMEA | NL & BE | All in NL & BE | The Geo FA was recently completed, resulting in a move to 7 high for the following jurisdictions: French Polynesia PF Palestine PS Togo TG Both NL & BE include the enterprise/consolidated list in their TM programme and as such need to have the risk scores for the above increased from a 7 to a 9 per market/regulatory requirement. | Anna De Nicolais |  | 2025-08-28 | Completed |  | Completed with CRR Customization Form CMC-2025-133 |  | Approved |  | No | 2025-08-29 15:00 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
172 | EU Third Countries List update | Change | High Risk Override | Regulatory Requirement | Sasha Hopkins | 2025-06-25 | EMEA | all in EMEA with exception of the UK & X1 | all in EMEA with exception of the UK & X1 | The EU Third Countries List was updated on the 10th June as follows: Added: Algeria, Angola, Côte d'Ivoire, Kenya, Laos, Lebanon, Monaco, Namibia, Nepal and Venezuela Removed: Barbados, Gibraltar, Jamaica, Panama, the Philippines, Senegal, Uganda, and the United Arab Emirates Please can you make these updates accordingly, with all jurisdictions being added requiring a risk score of 9 (if not already in place). For those jurisdictions being removed please see as follows: Gibraltar - to be reverted to natural risk score for all markets Barbados, Jamaica, Panama, Philippines, Senegal, Uganda, and United Arab Emirates - to be reverted to natural risk score for all markets. Where there are jurisdictions with an override in place, which do no appear in the currently certified HRJ lists please revert to natural risk score (unless otherwise directed). | Anna De Nicolais |  | 2025-08-28 | Completed |  | As per discussion on 8/26/25, CEE and Nordics are using the ES Local HRJ and Local Non Compliant lists only in the elements as they are applicable to only certain products (SE and CORP) and creating overrides in CADENCE will impact all products. This overrides CRR Customization Form 162 for CEE (KY removed). | Alex Redpath;#32;#Tommy Colbert;#20;#Wendy M Ward;#82;#Robert J Garcia;#117 | Approved |  | No | 2025-08-29 11:30 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
173 | UK Third Countries & Local List HRJ Update | Change | High Risk Override | Regulatory Requirement | Sasha Hopkins | 2025-06-25 | EMEA | UK & X1 | all in UK & X1 | The FATF list updated on 16th June 2025, and as such the UK Third Countries & Local Lists require update in line with this publication. Please can you make the following updates, with those jurisdictions being added requiring a risk score of 9 (if not already in place). The jurisdictions being removed should be reverted to their natural risk score. Added: Bolivia, British Virgin Islands Removed: Croatia, Mali, Tanzania | Anna De Nicolais |  | 2025-08-28 | Completed |  | Includes CRR Customization Form 161 | Alex Redpath;#32;#Tommy Colbert;#20;#Wendy M Ward;#82;#Robert J Garcia;#117 | Approved |  | No | 2025-08-29 11:28 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
180 | UK/X1 Integration of SBS in Geo of AH/BO | Change | Data Element Weighting Value | Best Practice | Anna De Nicolais | 2025-08-21 | EMEA | UK, X1 | SBS | Maestro / iRefresh utilize the customer level risk scoring while the EDD process continues to use the account risk scoring in CADENCE. There is a gap where the customer level score is “High” while none of the account level scores are “High”. | Anna De Nicolais | Geography of AH: This rule will add points based on the Geography of the Account Holder (except CONS and CORP products) This rule will add points based on the Geography of the Account Holder (CORP) This rule will add points based on the Geography of the Account Holder (CONS) This rule will add points based on the Geography of the Account Holder for non CONS, CORP and SBS. This rule will add points based on the Geography of the Account Holder for SBS for 01-Low rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 02-Low rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 03-Low rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 04-Medium rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 05-Medium rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 06-Medium rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 07-High rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 08-High rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 09-High rated geographies. Geography of BO: This rule will add points based on the Geography of the Beneficial Owners for non SBS This rule will add points based on the Geography of the Beneficial Owners for SBS for 01-Low rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 02-Low rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 03-Low rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 04-Medium rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 05-Medium rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 06-Medium rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 07-High rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 08-High rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 09-High rated geographies. | 2025-08-28 | Completed |  | Geography risk elements when a customer has both a consumer and SBS account have been run in sandboxes and will reduce the high-risk customers by nearly 2000 by integrating the SBS elements in the Geography of AH/BO elements. CMC-2025-134 | Joseph Usher;#513 | Approved |  | No | 2025-08-29 13:34 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
111 | Argentina HRO Removal | Remove | High Risk Override | Regulatory Requirement | Ricardo Linares Hernandez | 2024-04-24 | LACC | Argentina | All | In Argentina, the business only opens accounts for individuals or entities that demonstrate residence in the country (mostly domestic spending is expected), so from a risk-based approach it is necessary to identify relevant spending made at all countries flagged as high risk by the CADENCE methodology. Therefore, Argentina MCO team made a review of the recently refreshed Geography Fundamental Assessment and requests to remove all the overrides of 09-High to country risk rating and adhere to geographical assessment. COUNTRY Previous Risk Score Overrides AS 9 BD 9 BI 9 BO 9 BY 9 CD 9 CF 9 CG 9 CM 9 CN 9 CW 9 DJ 9 EG 9 ER 9 ET 9 FJ 9 GN 9 GQ 9 GT 9 GU 9 GW 9 HN 9 IN 9 IQ 9 KM 9 LA 9 LB 9 LY 9 MG 9 MR 9 MZ 9 NE 9 NG 9 NI 9 NP 9 PA 9 PK 9 PW 9 RU 9 SD 9 SO 9 SV 9 TD 9 TJ 9 TM 9 TT 9 TZ 9 VE 9 VI 9 VN 9 VU 9 WS 9 ZW 9 | Anna De Nicolais |  | 2025-09-17 | Completed |  | Completed with CRR Certification - CRR Customization Form 160, CMC-2025-137 | Gabriel Maximiliano N Abitbol;#156 | Approved |  | No | 2025-09-17 10:04 | Ricardo Linares Hernandez |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
159 | Certification - FR | Change | Data Element Weighting Value | Best Practice | Najat ElHamdi | 2025-03-17 | EMEA | France | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified and changes were made to meet local requirements and align with EMEA standards. More details in the attached documents. | Anna De Nicolais | Large No of Supp - Consumer accounts with >3 and <6 supps - 16: HRO: Consumer accounts => 6 supps - Integrate FRSHRO SIP-SIE Present on Account: - Add Char: SIE added to the file as part of SIP/SIE remediation - This rule adds point if there is a SIP or SIE on the account (add char) This rule adds point if there is a SIP present on the account Country on Local HRJ List - HRO for geography in HRJ Cross Border SpdCnt dif HRJ: reactivated to 200 points - 1: Cross Border Spend count of different HRJ <4 in last 12 months - 2: Cross Border Spend count of different HRJ >= 4 and >= 6 in last 12 months - from 6 to 3: Cross Border Spend count of different HRJ >6 in last 12 months Cross Border Spend Amount - zeroed out Cross Border Spend HRJ Amount: reactivated at 100 points - 1: Cross Border Spend in High Risk Country amount >=$5000 and <$10,000 in last 12 months - 2: Cross Border Spend in High Risk Country amount >= $10,000 USD and <$25,000 USD in last 12 months - 3: Cross Border Spend in High Risk Country amount >= $25,000 USD <$40,000 USD in last 12 months - 4: Cross Border Spend in High Risk Country amount >= $40,000 in last 12 months Cross Border Spend HRJ Count: from 600 to 300 points - 1: Cross Border Spend Count in High Risk Country count >5 in last 12 months The following actions were taken for Legacy HRO and ARFs: • FRLOCH, FRSHRO, HRO – Non-Cooperative Tax, BRGLST were integrated as elements. • BRGLST, FESTRA, FESTRN, FRLOCH, FRSHRO, GXTRA, GXTRN, TRNHRO, TRNARF and USCS02 to be decommissioned. Geography of Account Holder: This rule will add points based on the Geography of the Account Holder (CORP) This rule will add points based on the Geography of the Account Holder (CONS) This rule will add points based on the Geography of the Account Holder for non CONS, CORP and SBS. This rule will add points based on the Geography of the Account Holder for SBS for 01-Low rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 02-Low rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 03-Low rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 04-Medium rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 05-Medium rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 06-Medium rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 07-High rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 08-High rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 09-High rated geographies. Geography of Beneficial Owner: This rule will add points based on the Geography of the Beneficial Owners for non SBS This rule will add points based on the Geography of the Beneficial Owners for SBS for 01-Low rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 02-Low rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 03-Low rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 04-Medium rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 05-Medium rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 06-Medium rated geographie This rule will add points based on the Geography of the Beneficial Owners for SBS for 07-High rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 08-High rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 09-High rated geographies. Geography of AH/BO SBS: - zeroed out and incorporated into Geo of AH/BO due to Maestro issue | 2025-09-17 | Completed |  | CMC-2025-144 | Bruno Jeannoel VIGOGNE;#366 | Approved |  | No | 2025-09-25 07:50 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
160 | Certification - AR | Change | Data Element Weighting Value | Best Practice | Rocio Ayelen Berbetoros | 2025-03-18 | LACC | AR | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified and changes were made to meet local requirements and align with EMEA standards. More details in the attached documents. | Anna De Nicolais | Zip Code: Table Maintenance truncation of 5 created High Risk files changed to Enterpise CRR CF 111 in order to remove overrides Industry: - HROs added to Charity Industry Type to decommission CHARIT HRO Nationality of AH and Autorized Signer (AS added and rule aligned with ARNAT1/2/H) - from 1 to 6 mult: Nationality in medium risk country - from 3 to 12 mult: Nationality in high risk country (file changed to Enterpise CRR CF 111) - 80 mult: Nationality in CU, IR, KP, SY Nationality of BO (Autorized Signer removed and rule aligned with ARNAT1/2/H) - from 1 to 6 mult: Nationality in medium risk country - from 3 to 12 mult: Nationality in high risk country - 80 mult: Nationality in CU, IR, KP, SY PEP Risk Rating - from 3 to 20 mult: High Risk PEP to align with MX SIP-SIE Present on Account: - This rule adds point if there is a SIP or SIE on the account (SIP ADD Char data point added) Higher risk Postal Codes - Higher risk Postal Codes in AR: list provided to decommission 3BORDR to include both zip codes with letters and numbers, test sandbox - 0:Higher risk Postal Codes in US - 0: Higher risk Postal Codes in TH - 1:Higher risk Postal Codes in AR - 9: Higher risk Postal Codes in AR 3BORDR Prohibited Geographies: - from 1000 to 4000 to assign the maximum points to accounts in prohibited geo Legacy HROs and ARFs to be incorporated as an element: CHARIT, BRGLST, 3BORDR, ARNAT1, ARNAT2 and ARNATH. Legacy HROs and ARFs to be decommissioned: CHARIT, BRGLST, 3BORDR, ARNAT1, ARNAT2, ARNATH, FESTRA, FESTRN, GXTRA, GXTRN, TRNARF, TRNHRO, USCS02. | 2025-09-17 | Completed |  | Includes CRR Customization Form 111 - HRJ overrides removal CMC-2025-137 | Gabriel Maximiliano N Abitbol;#156 | Approved |  | No | 2025-09-17 10:31 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
184 | UK/X1 UK Third Country list correction | Add | High Risk Override | Best Practice | Anna De Nicolais | 2025-09-16 | EMEA | UK/X1 | All | AO, BF, CI, DZ, LA, LB, NP to be added | Anna De Nicolais | Notable Jurisdiction List: UK Third Country list correction by adding AO, BF, CI, DZ, LA, LB, NP. | 2025-09-18 | Completed |  | During the review of Geography changes it was identified that AO, BF, CI, DZ, LA, LB, NP were missing from the UK Third Country list. IS-5838 opened on 10/1/25. LB did not save in the list and was readded on 10/23/25. | Louise Emma Johnston;#132 | Approved |  | No | 2025-10-23 13:06 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
183 | US party roles: add CN Control Person (RP), EO Equity Owner (BO) - Project Oculus | Add | Data Element Weighting Value | Best Practice | Prateek Jain | 2025-09-16 | US | US | All | Project Oculus is introducing two new party roles that need to be added to the appropriate files. - CN Control Person (RP) - EO Equity Owner (BO) | Anna De Nicolais | Nationality of Beneficial Owner: - Medium - High Geography of Beneficial Owners Geography of Related Parties | 2025-09-19 | Completed |  | CMC-2025-160 | Tyler R Singley;#118 | Approved |  | No | 2025-09-22 14:15 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
167 | Certification - US | Change | Data Element Weighting Value | Best Practice | Kelly T Etherington | 2025-05-06 | US | US | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified, and changes were made to meet local requirements. More details in the attached documents. | Anna De Nicolais | • Length of Relationship element was modified by assigning points to relationships less than 24 months old, instead of 36 months old, with the following configuration: o 0: Customer's relationship is > 24 months o 1: Customer's relationship is >12 and <=24 months o 2: Customer's relationship is <=12 months • SIP-SIE Present on Account element was modified by adding SIE to the file in the Additional Characteristics data point, in order to capture Special Interest Entities (“SIE”). • Prohibited Geographies element weightage changed from 1000 to 4000 points, as accounts associated with prohibited geographies should get the maximum amount of points available. • Higher Risk Postal Codes in Country element was modified by removing the Thailand list of high risk postal codes, as not applicable to the market. • Merchant Returns Ratio element was activated with a weighting of 100 points and the following configuration: o 1: Merchant returns ratio between 0.0495 and 0.095 in the last 12 months o 2: Merchant returns ratio between 0.096 and 0.162 in the last 12 months o 3: Merchant returns ratio greater than or equal to 0.163 in the last 12 months • Wire Payment Source Country element was enhanced by adding PAY-ACH to the data point to capture PAY-ACH transactions. • BRGLST Legacy ARF3 to be incorporated as an element. • Legacy HRO/ARFs to be decommissioned: BRGLST, FESTRA, FESTRN, FORJUR, GXTRA, GXTRN, USCS02. | 2025-10-15 | Completed |  | CMC-2025-169 | Robert J Garcia;#117 | Approved |  | No | 2025-10-16 14:30 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
185 | Request to increase 3BORDR from ARF3 to HRO | Change | High Risk Override | Regulatory Requirement | Lucas Agustin Ferrari | 2025-10-08 | LACC | Argentina | All products | Request to increase the points assigned to accounts associated with postal codes 3370, M3370, N3370 (3BORDR) from an ARF3 (900 points) to an HRO (4000 points). This is based in internal alignment and a National Risk Evaluation on AML/TF/PF attached (page 84) | Anna De Nicolais | Higher Risk Postal Codes - 3BORDR: from ARF3 to HRO | 2025-10-15 | Completed |  | During Certification, 3BORDR HRO was integrated into the Higher Risk Postal Codes element assigning an ARF3 to accounts associated with 3370, M3370, N3370 postal codes. Local regulations indicate that those accounts should be reviewed due to the high AML risk in the area. The attached manual impact assessment indicates an increase of ~560 HR accounts. CMC-2025-178 | Gabriel Maximiliano N Abitbol;#156 | Approved |  |  | 2025-10-16 14:09 | Lucas Agustin Ferrari |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
187 | US - Spend Greater than Income correction | Remove | Data Element Weighting Value | Best Practice | Anna De Nicolais | 2025-10-20 | US | US | Consumer | Spend Greater than Income was not zeroed out when the Certification changes were implemented and needs to be corrected. | Anna De Nicolais | Spend Greater than Income decommissioned | 2025-10-20 | Completed |  | CMC-2025-182 This customization from has been created to retroactively capture the changes that were implemented immediately upon discovery of the error. The correction was implemented to production on 10/20/25. | Tommy Colbert;#20 | Approved |  | No | 2025-11-07 13:15 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
163 | Certification - CA | Change | Data Element Weighting Value | Best Practice | Antonella P Keating | 2025-03-25 | LACC | CA | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified and changes were made to meet local requirements. More details in the attached documents. | Anna De Nicolais | HROEMD: - integrated. BRGLST: - integrated. Occupation (Job code): - Risk rating for Occupation Job Description Consumer and SBS - 0 points for all products except Consumer and SBS - File to include Individual products: added CORP-CARD, BANK-PLEND, SING-PER PEP Foreign: - Wt. changed from 200 to 4000 PEP Risk rating: - Multiplier changed from 3 to 20 for High risk PEPs SIP-SIE Present on Account: - Add Char: SIE added to the file as part of SIP/SIE remediation. Higher Risk Pstlcds in country: - US and TH zeroed out Higher Risk Rgns within cntry: - zeroed out Spend Greater than Income: - Element activated as required by local regulations Decommissioned BRGLST, FESTRA, FESTRN, GXTRA, GXTRN, TRNARF, TRNHRO, USCS02. Occupation Descriptions: - CSV file doesn't distinguish between French alphabet and modified characters (i.e. Sécurité Aérienne and Sï¿½curitï¿½ Aï¿½rienne) and are read as duplicates when both variations are present preventing the file to be saved in the data point, therefore only one option in file based on data pull. | 2025-11-06 | Completed |  | CMC-2025-159 | Scott Burton Selig;#548 | Approved |  | No | 2025-11-07 09:42 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
177 | PEP and SIP modification for CORP Products (except CORP-CTRL and CORP-LGT) | Change | Data Element Weighting Value | Best Practice | Sasha Hopkins | 2025-08-01 | EMEA | Italy | CORP Products (except CORP-CTRL and CORP-LGT) | CORP Products (except CORP-CTRL and CORP-LGT) limited to AH to avoid PEP/SIP/SIE points to be cascaded to all accounts under the corporation. | Anna De Nicolais | PEP Present: - This will add points if a PEP is present on the customer accounts (CORP products other than CORP-CTRL and CORP-LGT) - AH only - This will add points if a PEP is present on the customer accounts (except CORP products other than CORP-CTRL and CORP-LGT) SIP/SIE Present: - This rule adds point if there is a SIP present on the account (CORP products other than CORP-CTRL and CORP-LGT)- AH only This rule adds point if there is a SIP or SIE on the account (add char - except CORP products other than CORP-CTRL and CORP-LGT) - This rule adds point if there is a SIP present on the account (except CORP products other than CORP-CTRL and CORP-LGT) - This rule adds point if there is a SIP or SIE on the account (add char - CORP products other than CORP-CTRL and CORP-LGT) - AH only | 2025-11-17 | Completed |  | CMC-2025-187. Completed with CRR Customization Form 179. Rule created for CORP products (except CORP-CTRL and CORP-LGT) limited to AH to avoid PEP/SIP/SIE points to be cascaded to all accounts under the corporation. | Valentina Finazzo;#409 | Approved |  | No | 2025-11-17 14:05 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
179 | Italy - Revised SBS Approach & Address Type testing | Change | Data Element Weighting Value | Best Practice | Sasha Hopkins | 2025-08-28 | EMEA | Italy | All in Italy | As you will likely recall, post the RBA migration last year there were multiple issues raised which were impacting the risk scoring for Italy – we have regrouped with the MCO & OE and, now that audit for the market has started again, we are revisiting to outstanding items to push for updates and/or resolution where possible. As is the case for wider EMEA, the SBS product is disproportionately being impacted in the CRR (particularly in the medium risk bucket) by virtue of the fact they trigger both the individual and the entity. To address this impact for Italy, and then subsequently the rest of EMEA, we would like to test the approach recently implemented by the UK and amend the following elements; Nationality – amended both Nationality of Account Holder and Beneficial Owner elements for the SBS product only, with Account Holder receiving 30 points and Beneficial Owner receiving 20 points so as to align with the Consumer scoring of 50 for Account Holder. Geography – amended the three geography elements with the same principle as Nationality for the SBS products only – Geography of Account Holder receiving 60 points, Geography of Beneficial Owner receiving 25 points, Geography of Related Parties receiving 15 points.” Separately we would also ask to test limiting the Geography of Account Holder rule to exclude B for consumer products as this is adversely impacting customer risk scores. As per conversation we hope testing can begin in early September. | Anna De Nicolais | Geography of Account Holder: This rule will add points based on the Geography of the Account Holder (CONS) -Address usage B removed This rule will add points based on the Geography of the Account Holder for non CONS and SBS. This rule will add points based on the Geography of the Account Holder for SBS for 01-Low rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 02-Low rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 03-Low rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 04-Medium rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 05-Medium rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 06-Medium rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 07-High rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 08-High rated geographies. This rule will add points based on the Geography of the Account Holder for SBS for 09-High rated geographies. Geography of Beneficial Owner: This rule will add points based on the Geography of the Beneficial Owners for non SBS This rule will add points based on the Geography of the Beneficial Owners for SBS for 01-Low rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 02-Low rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 03-Low rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 04-Medium rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 05-Medium rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 06-Medium rated geographie This rule will add points based on the Geography of the Beneficial Owners for SBS for 07-High rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 08-High rated geographies. This rule will add points based on the Geography of the Beneficial Owners for SBS for 09-High rated geographies. | 2025-11-17 | Completed |  | CMC-2025-187. Implemented with CRR Customization Form 177. We run the sandbox with the changes to Geography of AH/BO for SBS products, as this is associated with the MAESTRO/medium risk reviews issue. Changes to the Nationality element for SBS will need further discussion due its complexity and creating additional issues in MAESTRO. | Valentina Finazzo;#409 | Approved |  | No | 2025-11-17 14:08 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
192 | FATF and UK High Risk Third updates - OCT 25 | Change | Data Element Weighting Value | Best Practice | Anna De Nicolais | 2025-11-25 | Global | All (except EMEA) | All | On October 24, 2025, the FATF and UK High Risk Third lists were updated and Burkina Faso, Mozambique, Nigeria and South Africa were removed. | Anna De Nicolais | All elements relying on geography files. | 2025-12-02 | Completed |  | EMEA region was not impacted because Burkina Faso, Mozambique, Nigeria and South Africa remain on the EU Third Country List and geography dependent files were maintained. | Natalia E Gonzalez;#196;#Robert J Garcia;#117;#Wendy M Ward;#82 | Approved |  | No | 2025-12-02 15:50 | Anna De Nicolais |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
117 | CRR - Request change in High Risk Jurisdictions | Change | Data Element Weighting Value | Regulatory Requirement | Amit Sehgal | 2024-06-26 | APAC | India | Consumer- Credit, Consumer - Charge, Corporate - CPC, Corporate - BTA, Corporate - Card, Corporate - LGT, SE- DIrect and Bank - BTERM | The FIU-IND has changed the list of high risk states in India. Hence we would request the parameter' Higher risk states within country' to be changed for states that are now considered as High risk states within country. The list of states now include are: a. JK – Jammu & Kashmir (including Leh & Ladakh) b. AS – Assam c. AR- Arunachal Pradesh d. MN – Manipur e. ML – Meghalaya f. MZ - Mizoram g. NL – Nagaland h. TR - Tripura The weighting to be set to 100 and a multiplier of 1. Additionally, the Higher Risk Pstlcds in country element will be updated with a new list of postal codes. Weighting and applicability will remain the same. | Richa Khullar |  | 2026-01-05 | Completed |  | Sandbox run to identify the impact. To be closed with Certification as the list has been updated and the attached is no longer valid. CRR Customization Form 182, CMC-2025-166 | Ritin Prakash;#169 |  |  | No | 2026-01-23 12:21 | Aditi Nanda |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
182 | Certification - IN | Change | Data Element Weighting Value | Best Practice | Amit Sehgal | 2025-09-05 | APAC | India | All | The Certification process was conducted to review rules and settings to ensure that they are working as intended and meet local regulatory requirements. Areas for improvement were identified, and changes were made to meet local requirements and align with APAC standards. More details in the attached documents. | Richa Khullar | Industry -Industry type CONSTRUCT aligned to the enterprise approach – risk score changed from 7 to 1. SIP-SIE: - file updated to include SIE. Spend Greater than Income - Element reactivated with enterprise thresholds and the rule sets below: - Consumer - Spend between 50 and 75 percent of annual income - Consumer - Spend between 75 and 100 percent of annual income - Consumer - Spend greater than 100 percent of income BRGLST - Integrated Higher Risk Postal Codes in Country - Removed for US and TH as not applicable to market - Postal codes list updated for IN rule HRO/ARFs to be decommissioned: - BRGLST, FESTRA, FESTRN, GXTRA, GXTRN, TRNARF, TRNHRO. | 2026-01-05 | Completed |  | MCO requested to remove the override for - Risk rating for industry code M8651(political organizations) on 11/24/25 to align with Enterprise. MCO also requested to cancel the proposed increase from 1 to 7 to Occupation Type code 'Home Maker'. | Vineet D Dhamija;#87;#Ritin Prakash;#169 | Approved |  | No | 2026-01-21 09:08 | Richa Khullar |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
191 | UK HRI - high impacting code removal | Remove | High Risk Override | Best Practice | Sasha Hopkins | 2025-11-12 | EMEA | UK & X1 | All in UK & X1 | As previously discussed and as per escalation from the UK market & the Country Manager we are requesting to remove the following codes from the UK HRI list and no longer subject them to HRO: USIC64301 FIN-STOCK (mult. : 8) Investment trusts USIC64304 FIN-STOCK (mult. : 8) open end investment companies USIC66300 PROF-SERV (mult. : 8) Fund management USIC69202 PROF-SERV (mult. : 8) Book keeping USIC69203 PROF-SERV (mult. : 8) Tax consultancy USIC70221 PROF-SERV (mult. : 8) Financial management Attaching the alignment with the MCO - please can you confirm timeframes for testing and implementation? | Swapnil Gupta | Removed the following industry codes from the Industry Code HRO file: USIC64301 USIC64304 USIC66300 USIC69202 USIC69203 USIC70221 Those codes went from receiving 4000 points to 320 points (40 x 8 = 320), loosing 3680 points. More details in the attached impact assessment. | 2026-01-05 | Completed |  | CMC-2025-202 | Joseph Usher;#513 | Approved |  | No | 2026-01-05 10:39 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form
169 | FR Local List - HRJ | Change | High Risk Override | Regulatory Requirement | Sasha Hopkins | 2025-05-23 | EMEA | FR | All in FR | As per email from MCO the FR local list has changed during the certification process, removing the following jurisdictions: • Bahamas • Belize • Seychelles The new list was currently in testing per the certification process, and wider geography changes are currently being completed, so please let us know best steps for removing these jurisdictions from the updated list. | Swapnil Gupta | BS - Bahamas (9 to 4 risk score), BZ - Belize (9 to 5 risk score) and SC - Seychelles (9 to 4 risk score) were removed from the Country on Local HRJ element and a manual impact assessment was performed. Need to remove 9 overrides IN CADENCE and revert to natural risk score. Following elements were modified: Nationality of Account Holder Nationality of Beneficial Owner Country on Local HRJ List Geography of Account Holder(SBS - 4/5/9) Geography of Beneficial Owner(SBS - 4/5/9) ATM Withdrawals Foreign Count Cross Border SpndCnt dif HRJ Cross Border Spend HRJ Amount Cross Border Spend HRJ Count Wire Payment Source Country Foreign bank ACH/DD Count Wire Payment Foreign Count | 2026-01-21 | Completed |  | CMC-2025-204 | Stefano Malinconico;#650 | Approved |  | No | 2026-01-21 11:22 | Sasha Hopkins |  | Item | teams/GFCC-RMO/Lists/CRR Customization Form