## CRR PRD 2026 (WIP)
Formatted ID | Name | Release | Custom Field 3 | Planned Start Date | Planned End Date
F776672 | CRR - Data Requests from FC-COE Team - in E1 & E2 (Analysis) | AXP PI 26.1 | BRD 12.4.2 | 01/20/2026 12:00 AM MST | 03/30/2026 11:59 PM MST
F817940 | CRR - Enable Asset manager functionality E2E ( Analysis & Build) E2 | AXP PI 26.1 | BRD 12.6.1 | 01/20/2026 12:00 AM MST | 03/30/2026 11:59 PM MST
F717264 | CRR - Event Based Rule Triggers in E1 (Analysis, Build) | AXP PI 26.1 | BRD 12.16 | 01/20/2026 12:00 AM MST | 03/30/2026 11:59 PM MST
F811673 | CRR - Incremental variables for Merchant (Consume & Validate) in E1 | AXP PI 26.1 | BRD 12.8 | 01/20/2026 12:00 AM MST | 03/02/2026 11:59 PM MST
F717260 | CRR - Rule Change Based Rule Triggers in E1 (Analysis, Build) | AXP PI 26.1 | BRD 12.16.1 | 01/20/2026 12:00 AM MST | 03/30/2026 11:59 PM MST
F717259 | CRR - Time Based Rule Triggers in E1 (Analysis, Build) | AXP PI 26.1 | BRD 12.16 | 01/20/2026 12:00 AM MST | 03/30/2026 11:59 PM MST
F817939 | CRR - UI Enhancements & modifications and miscellaneous work in E2 | AXP PI 26.1 | BRD 12.9 | 01/20/2026 12:00 AM MST | 03/30/2026 11:59 PM MST
F817944 | CRR - Unified Sandbox Configuration Experience (UI & Journey Revamp) | AXP PI 26.1 | BRD 12.10 | 01/20/2026 12:00 AM MST | 03/30/2026 11:59 PM MST
F823017 | CRR -Re-procure E1 and E2 Cloud SQL | AXP PI 26.1 | BRD 12.8.1;12.8.7;12.8.15 | 01/20/2026 12:00 AM MST | 03/02/2026 11:59 PM MST
F817942 | CRR - Enable Fundamental Assessment functionality E2E in E2 | AXP PI 26.2 | BRD 12.4.1 | 06/10/2025 12:00 AM MST | 08/04/2025 11:59 PM MST
F818239 | CRR - Entity variables for SBS, Corp & Digital Banking (Consume & Validate) in E2 | AXP PI 26.2 | BRD 12.8 | 08/19/2025 12:00 AM MST | 10/27/2025 11:59 PM MST
F818237 | CRR - Event based Trigger (Launch in E2) | AXP PI 26.2 | BRD 12.16 |  | 10/13/2025 11:59 PM MST
F797427 | CRR - Incremental variables for Merchant (Consume & Validate) in E2 | AXP PI 26.2 | BRD 12.8 | 08/19/2025 12:00 AM MST | 10/27/2025 11:59 PM MST
F717266 | CRR - Rule change based Trigger (Launch in E2) | AXP PI 26.2 | BRD 12.16 |  | 10/13/2025 11:59 PM MST
F817953 | CRR - Simulation Functionality modernization ( Analysis & Build) E2 | AXP PI 26.2 | BRD 12.4.1 | 06/10/2025 12:00 AM MST | 08/04/2025 11:59 PM MST
F818238 | CRR - Time based Trigger (Launch in E2) | AXP PI 26.2 | BRD 12.16 |  | 10/13/2025 11:59 PM MST
F825062 | CRR - UI Enhancements & modifications 26.2 | AXP PI 26.2 | BRD 12.16 |  | 10/13/2025 11:59 PM MST
Backlog | CRR - Audit functionality modernization ( Analysis ) E2 PI 26.3 | AXP PI 26.3 | BRD 12.4.1 | 06/10/2025 12:00 AM MST | 08/04/2025 11:59 PM MST
F817949 | CRR - Update Functionality ( Analysis ) E2 PI 26.2 | AXP PI 26.2 | BRD 12.4.1 | 06/10/2025 12:00 AM MST | 08/04/2025 11:59 PM MST
F762607 | CRR - Account, Customer & Hierarchy Scoring as per POA Individual logic in E1 | AXP PI 26.3 | BRD 12.8.1;12.8.7;12.8.15 | 10/27/2025 12:00 AM MST | 11/27/2025 11:59 PM MST
F817956 | CRR - Audit functionality modernization ( Analysis & Build) E2 PI 26.3 | AXP PI 26.3 | BRD 12.4.1 | 06/10/2025 12:00 AM MST | 08/04/2025 11:59 PM MST
F776126 | CRR - Corporate & SBS Entity Variables Consume, Validate, Calculate CRR E1/E2 (Build & Test) | AXP PI 26.3 | BRD 12.8 |  | 10/13/2025 11:59 PM MST
F794655 | CRR - Data Standarization for Categorical variables E1/E2 (Build & Deploy) | AXP PI 26.3 | BRD 12.8
F803432 | CRR - Design framework to maintain CRR change log | AXP PI 26.3 |  | 10/28/2025 12:00 AM MST
F812361 | CRR - E3 Readiness PI26.3 | AXP PI 26.3 | BRD 12.8 | 01/20/2026 12:00 AM MST | 03/30/2026 11:59 PM MST
F825042 | CRR - POC for Authourization of CRR Capabilities -PI 26.2 | AXP PI 26.3 | BRD 12.21 | 11/10/2025 12:00 AM MST | 01/05/2026 11:59 PM MST
F833055 | CRR - Simulation Functionality modernization UI enhancements E2 | AXP PI 26.3 | BRD 12.4.1 | 06/10/2025 12:00 AM MST | 08/04/2025 11:59 PM MST
F833056 | CRR - Update Functionality UI enhancements E2 | AXP PI 26.3 | BRD 12.4.1 | 06/10/2025 12:00 AM MST | 08/04/2025 11:59 PM MST
F736570 | CRR Kabbage/WCT/Term Loans Variables - ( Consume & Validate) in E2 | AXP PI 26.3 | BRD 12.8 |  | 10/13/2025 11:59 PM MST
F736574 | CRR Personal Saving Account Variables Consume, Validate, Calculate CRR (Build & Test) | AXP PI 26.3 | BRD 12.8 |  | 10/13/2025 11:59 PM MST
F833070 | CRR - Account, Customer & Hierarchy Scoring as per POA Individual logic in E2 | AXP PI 26.4 | BRD 12.8.1;12.8.7;12.8.15 | 10/27/2025 12:00 AM MST | 11/27/2025 11:59 PM MST
F817976 | CRR - Authourization of CRR Capabilities - (Build) E2 PI 26.4 | AXP PI 26.4 | BRD 12.21 | 11/10/2025 12:00 AM MST | 01/05/2026 11:59 PM MST
F818241 | CRR - Entity variables for SBS, Corp & Digital Banking (Consume & Validate) in E3 | AXP PI 26.4 | BRD 12.8 | 08/19/2025 12:00 AM MST | 10/27/2025 11:59 PM MST
F757389 | CRR - Notifications & Smart Alerts | AXP PI 26.4 | BRD 12.18
F797421 | CRR - Obligor Scoring for Entity Products in E1 | AXP PI 26.4 | BRD 12.4
F776676 | CRR - Sandbox & Simulation in E3 ( Individual ) | AXP PI 26.4 | BRD 12.8 |  | 10/13/2025 11:59 PM MST
F776132 | CRR ¦BCA,CCA,Prepaid(Serve,BOL) Variables Consume, Validate, Calculate CRR (Build & Test) | AXP PI 26.4 | BRD 12.8 |  | 10/13/2025 11:59 PM MST
F776168 | CRR ¦Non-card Variables Consume, Validate, Calculate CRR (Build & Test) | AXP PI 26.4 | BRD 12.8 |  | 10/13/2025 11:59 PM MST
F797423 | CRR - Account, Customer & Hierarchy Scoring as per existing logic for Individual in E3 (Deploy and Test) | AXP PI 26.5 | BRD 12.8.1;12.8.7;12.8.15 | 10/27/2025 12:00 AM MST | 11/27/2025 11:59 PM MST
F797418 | CRR - Authourization of various functionalities in E3 (Build, Test, Validate) | AXP PI 26.5 | BRD 12.21
F716854 | CRR - Certification & Extraction of underlying changes to CRR Framework | AXP PI 26.5 | BRD 12.11 |  | 10/13/2025 11:59 PM MST
F797430 | CRR - Data Standarization for Categorical variables E3 (Build & Deploy) | AXP PI 26.5 | BRD 12.8
F797440 | CRR - Deployment of CRR Dashboards in E2 | AXP PI 26.5 | BRD 12.9.2
F776674 | CRR - Historical Data migration | AXP PI 26.5 | BRD 12.15
F717281 | CRR - Integration with downstream apps (KYC, AML, TM, EDD) | AXP PI 26.5 | BRD 12.12
F717280 | CRR - Manual Overrides for Risk score by authorized users | AXP PI 26.5 | BRD 12.16
F833072 | CRR - Obligor Scoring for Entity Products in E2 | AXP PI 26.5 | BRD 12.4
F716859 | CRR - Change Request Process Enablement in E2 ( PI 27.1) | AXP PI 27.1 | BRD 12.2
F757382 | CRR - Incorporation of Transaction model element in CRR Calculations | AXP PI 27.1 | BRD 12.9
F757388 | CRR - Onboarding-Real-Time Customer Risk scoring for new customer onboarding | AXP PI 27.1 | BRD 12.9
F797428 | CRR - Sandbox & Simulation in E3 ( Entity ) | AXP PI 27.1 | BRD 12.8 |  | 10/13/2025 11:59 PM MST
F736672 | CRR - End to End Data availability for CRR outside of GCIP on Lumi | AXP PI 27.2
F717277 | CRR - Production CRR Assessment Execution- Rule based (Deploy & Test) | AXP PI 27.2 | BRD 12.4 |  | 10/13/2025 11:59 PM MST
F736605 | CRR - Roll Out of CRR in Production for Validation | AXP PI 27.2 | BRD 12.17.2 ; BRD 12.17.3

## missing
Sandbox - Analysis of Results : System should provide the ability for users to review results from simulation exercises for better decision making and analytics
Customer level CRR view / Report: System should be able to provide the risk rating for a particular customer as well as make available the contributing factors that resulted in that rating
Performance Reporting ( DMO enabled)
CRR Certification : System should have the capability to facilitate CRR certification